## Product Backlog
Assignment 1: Agile Project Planning - Create a one-page project plan for a new software feature using Agile planning techniques. Include backlog items with estimated story points and a prioritized list of user stories.
Online Banking System
ProductBacklogID | Priority | UserStoryID | User story name | Scrum team assigned | Risk | Complexity | Type | Completeness Criteria | Comments
1 | High | U001 | User Authentication and Security | Anjali | High | High | Functional | Complete
As a user, I want to be able to create an account securely.
As a user, I want to be able to log in securely using multi-factor authentication.
As a user, I want my sensitive data (such as passwords and account information) to be encrypted and stored securely.
As a user, I want the system to detect and prevent unauthorized access or suspicious activity on my account.
2 | High | U002 | Account Management | Anjali | High | High | Functional | Complete
As a user, I want to be able to view my account balances.
As a user, I want to be able to see a list of transactions on each of my accounts.
As a user, I want to be able to transfer funds between my accounts.
As a user, I want to be able to link external accounts for easy fund transfers.
As a user, I want to be able to request account statements.
3 | High | U003 | Payments and Transfers | Anjali | High | High | Functional | Complete
As a user, I want to be able to make payments to other users or merchants.
As a user, I want to be able to set up recurring payments.
As a user, I want to be able to schedule future-dated payments.
As a user, I want to be able to initiate wire transfers domestically and internationally.
4 | High | U004 | Bill Management | Anjali | Low | Low | Functional | Complete
As a user, I want to be able to view and pay my bills online.
As a user, I want to be able to set up automatic bill payments.
As a user, I want to be able to receive notifications for upcoming bills.
5 | Low | U005 | Customer Support | Anjali | Low | Low | Functional | Pending
As a user, I want to be able to contact customer support through multiple channels (such as chat, email, or phone).
As a user, I want to be able to view FAQs and other self-help resources.
As a user, I want to be able to submit and track support tickets.
6 | High | U006 | Mobile Banking | Anjali | High | High | Functional | Complete
As a user, I want to be able to access all banking functionalities through a mobile app.
As a user, I want the mobile app to be user-friendly and responsive on various devices.
As a user, I want to be able to receive push notifications for important account activities.
7 | Low | U007 | Account Settings and Preferences | Anjali | High | Low | Functional | Pending
As a user, I want to be able to update my personal information (such as contact details).
As a user, I want to be able to customize my account preferences (such as notification settings).
As a user, I want to be able to manage security settings (such as changing passwords or updating security questions).
8 | Low | U008 | Reports and Analytics | Anjali | Low | Low | Functional | Pending
As a user, I want to be able to view detailed reports on my spending habits.
As a user, I want to be able to analyze my financial data to make informed decisions.
As a user, I want to be able to export financial data for tax or budgeting purposes.
9 | Low | U009 | Integration with Third-Party Services | Anjali | High | High | Functional | Pending
As a user, I want to be able to integrate my banking data with personal finance management tools.
As a user, I want to be able to link my accounts with payment gateways for online shopping.
10 | Low | U010 | Accessibility and Compliance | Anjali | Low | High | Functional | Complete
As a user, I want the online banking system to be accessible to people with disabilities.
As a user, I want the system to comply with relevant regulations and security standards.

## Sprint Backlog 1
ProductBacklogID | UserStoryID | UserStoryStepNo. | Task Description | Assigned To | Assigned Date | Estimate time | Status | Actual Time
1 | U001 |  | 1. User Authentication and Security | Durga | 2024-05-01 | 3 Days | Complete | 4 Days
|  | 1 | Task 1: Implement user registration functionality with input validation and encryption for storing passwords securely.
|  | 2 | Task 2: Integrate multi-factor authentication (MFA) using SMS verification for user logins.
|  | 3 | Task 3: Set up logging and monitoring to detect and prevent unauthorized access attempts.
2 | U002 |  | 2. Account Management | Vikas | 2024-05-05 | 4 Days | Complete | 4 Days
|  | 1 | Task 4: Develop UI components to display account balances and transaction history.
|  | 2 | Task 5: Implement backend logic for transferring funds between accounts.
|  | 3 | Task 6: Design and implement APIs for linking external accounts securely.
3 | U003 |  | 3. Payments and Transfers | Dattu | 2024-05-09 | 4 Days | Complete | 3 Days
|  | 1 | Task 7: Implement UI for initiating payments to other users or merchants.
|  | 2 | Task 8: Develop back-end logic for processing recurring and future-dated payments.
|  | 3 | Task 9: Integrate with payment gateways for wire transfers.

## Sprint Backlog 2
ProductBacklogID | UserStoryID | UserStoryStepNo. | Task Description | Assigned To | Assigned Date | Estimate time | Status | Actual Time
4 | U004 |  | 4. Bill Management | Sagar | 2024-05-15 | 4 Days | Complete | 3 Days
|  | 1 | Task 10: Design UI for viewing and paying bills online.
|  | 2 | Task 11: Implement back-end logic for scheduling automatic bill payments.
|  | 3 | Task 12: Set up notification system for reminding users of upcoming bills.
5 | U005 |  | 5. Customer Support | Durga | 2024-05-19 | 3 Days | Pending | 4 Days
|  | 1 | Task 13: Develop chat support feature and integrate with existing customer support platform.
|  | 2 | Task 14: Create FAQ section and populate with common questions and answers.
|  | 3 | Task 15: Implement UI for submitting and tracking support tickets.
6 | U006 |  | 6. Mobile Banking | Shruti | 2024-05-22 | 4 Days | Complete | 4 Days
|  | 1 | Task 16: Develop mobile app UI screens for accessing account functionalities.
|  | 2 | Task 17: Implement responsive design for various screen sizes and devices.
|  | 3 | Task 18: Set up push notification service for sending account activity alerts.

## Sprint Backlog 3
ProductBacklogID | UserStoryID | UserStoryStepNo. | Task Description | Assigned To | Assigned Date | Estimate time | Status | Actual Time
| U007 |  | 7. Account Settings and Preferences | Anjali | 2024-05-29 | 2 Days | Pending | 3 Days
7 |  | 1 | Task 19: Design UI for updating personal information and account preferences.
|  | 2 | Task 20: Implement back-end API endpoints for managing account settings.
|  | 3 | Task 21: Develop UI for changing passwords and security questions.
8 | U008 |  | 8. Reports and Analytics | Vikas | 2024-06-01 | 2 Days | Pending | 3 Days
|  | 1 | Task 22: Implement back-end logic for generating spending habit reports.
|  | 2 | Task 23: Design UI components for visualizing financial data.
|  | 3 | Task 24: Develop export functionality for downloading financial data in CSV format.
9 | U009 |  | 9. Integration with Third-Party Services | Dattu | 2024-06-03 | 3 Days | Pending | 4 Days
|  | 1 | Task 25: Integrate with personal finance management APIs for data synchronization.
|  | 2 | Task 26: Develop API endpoints for linking accounts with payment gateways.
10 | U010 |  | 10. Accessibility and Compliance | Shruti | 2024-06-06 | 5 Days | Complete | 4 Days
|  | 1 | Task 27: Conduct accessibility audit and implement necessary changes for compliance.
|  | 2 | Task 28: Review security measures to ensure compliance with relevant regulations.

## Sprint Planning All
Sprint No. | Goal | Duration | Start Date | End Date | Team Capacity | Backlog Items Selected | Tasks Breakdown and Assignments | Daily Standup Meetings | Demo and Review | Retrospective | Additional Notes
Sprint 1 | The goal of Sprint 1 is to establish a secure foundation for the online banking system and implement essential functionalities for user authentication, account management, and basic transactions. | 2 weeks | 2024-05-01 | 2024-05-14 | Frontend Developer: 80 hours Backend Developer: 80 hours UI/UX Designer: 40 hours QA Engineer: 40 hours Scrum Master/Product Owner: Part-time | User Authentication and Security Task 1: Implement user registration functionality with input validation and encryption for storing passwords securely. Task 2: Integrate multi-factor authentication (MFA) using SMS verification for user logins. Task 3: Set up logging and monitoring to detect and prevent unauthorized access attempts. Account Management Task 4: Develop UI components to display account balances and transaction history. Task 5: Implement backend logic for transferring funds between accounts. Task 6: Design and implement APIs for linking external accounts securely. Payments and Transfers Task 7: Implement UI for initiating payments to other users or merchants. Task 8: Develop backend logic for processing recurring and future-dated payments. Task 9: Integrate with payment gateways for wire transfers. | Frontend Developer: Tasks 1, 4, 7 Backend Developer: Tasks 2, 5, 8 UI/UX Designer: Tasks related to UI design and wireframes. QA Engineer: Testing tasks for each implemented functionality. | Time: 9:00 AM Duration: 15 minutes Purpose: Discuss progress, obstacles, and plans for the day. | Date: May 13th Time: 10:00 AM Duration: 1 hour Purpose: Review implemented features, gather feedback, and plan adjustments for the remaining sprint duration. | Date: May 14th Time: 10:00 AM Duration: 1 hour Purpose: Reflect on the sprint, identify what went well and what could be improved, and plan action items for the next sprint. | Daily burndown chart will be maintained to track progress. Continuous communication among team members via Slack or any preferred communication tool. Any impediments will be raised during daily standups and addressed promptly by the Scrum Master.
Sprint 2 | The goal of Sprint 2 is to enhance account management functionalities, implement bill management features, and start work on customer support and mobile banking. | 2 weeks | 2024-05-15 | 2024-05-28 | Frontend Developer: 80 hours Backend Developer: 80 hours UI/UX Designer: 40 hours QA Engineer: 40 hours Scrum Master/Product Owner: Part-time | Account Management Task 1: Implement UI for linking external accounts securely. Task 2: Enhance transaction history UI to include filtering and search functionality. Task 3: Develop backend logic for setting up account alerts and notifications. Bill Management Task 4: Design UI for viewing and paying bills online. Task 5: Implement backend logic for scheduling automatic bill payments. Task 6: Set up notification system for reminding users of upcoming bills. Customer Support Task 7: Implement chat support feature and integrate with existing customer support platform. Task 8: Create FAQ section and populate with common questions and answers. Task 9: Develop UI for submitting and tracking support tickets. Mobile Banking Task 10: Develop mobile app UI screens for accessing account functionalities. Task 11: Implement responsive design for various screen sizes and devices. Task 12: Set up push notification service for sending account activity alerts. | Frontend Developer: Tasks 1, 2, 4, 10 Backend Developer: Tasks 3, 5, 6 UI/UX Designer: Tasks related to UI design and wireframes for customer support and mobile banking. QA Engineer: Testing tasks for each implemented functionality. | Time: 9:00 AM Duration: 15 minutes Purpose: Discuss progress, obstacles, and plans for the day. | Date: May 13th Time: 10:00 AM Duration: 1 hour Purpose: Review implemented features, gather feedback, and plan adjustments for the remaining sprint duration. | Date: May 14th Time: 10:00 AM Duration: 1 hour Purpose: Reflect on the sprint, identify what went well and what could be improved, and plan action items for the next sprint. | Daily burndown chart will be maintained to track progress. Continuous communication among team members via Slack or any preferred communication tool. Any impediments will be raised during daily standups and addressed promptly by the Scrum Master.
Sprint 3 | The goal of Sprint 3 is to focus on enhancing security features, integrating with third-party services, and implementing additional functionalities based on user feedback. | 2 weeks | 2024-05-29 | 2024-06-11 | Frontend Developer: 80 hours Backend Developer: 80 hours UI/UX Designer: 40 hours QA Engineer: 40 hours Scrum Master/Product Owner: Part-time | Security Enhancements Task 1: Implement additional security checks for user authentication. Task 2: Enhance logging and monitoring system for detecting suspicious activities. Task 3: Conduct security audit and implement any necessary fixes. Integration with Third-Party Services Task 4: Integrate with personal finance management APIs for data synchronization. Task 5: Develop API endpoints for linking accounts with payment gateways. Additional Functionalities Task 6: Implement feature to view detailed reports on spending habits. Task 7: Develop functionality for analyzing financial data to make informed decisions. Task 8: Enhance accessibility features based on feedback and audit results. | Frontend Developer: Tasks 1, 6 Backend Developer: Tasks 2, 4, 5 UI/UX Designer: Tasks related to UI design and wireframes for security enhancements and additional functionalities. QA Engineer: Testing tasks for each implemented functionality. | Time: 9:00 AM Duration: 15 minutes Purpose: Discuss progress, obstacles, and plans for the day. | Date: May 13th Time: 10:00 AM Duration: 1 hour Purpose: Review implemented features, gather feedback, and plan adjustments for the remaining sprint duration. | Date: May 14th Time: 10:00 AM Duration: 1 hour Purpose: Reflect on the sprint, identify what went well and what could be improved, and plan action items for the next sprint. | Daily burndown chart will be maintained to track progress. Continuous communication among team members via Slack or any preferred communication tool. Any impediments will be raised during daily standups and addressed promptly by the Scrum Master.

## Kanban
To-Do | Work-in-progress | Complete
Payments and Transfers | Account Management | User Authentication and Security
Bill Management | Mobile Banking | Account Settings and Preferences
Customer Support | Reports and Analytics
Integration with Third-Party Services
Accessibility and Compliance

## Sprint Planning
Sprint Planning for Sprint 1 | Sprint Planning for Sprint 2 | Sprint Planning for Sprint 3
Sprint Goal: The goal of Sprint 1 is to establish a secure foundation for the online banking system and implement essential functionalities for user authentication, account management, and basic transactions. | Sprint Goal: The goal of Sprint 2 is to enhance account management functionalities, implement bill management features, and start work on customer support and mobile banking. | Sprint Goal: The goal of Sprint 3 is to focus on enhancing security features, integrating with third-party services, and implementing additional functionalities based on user feedback.
Duration: 2 weeks (From May 1st to May 14th) | Duration: 2 weeks (From May 15th to May 28th) | Duration: 2 weeks (From May 29th to June 11th)
Team Capacity: | Team Capacity: | Team Capacity:
Frontend Developer: 80 hours | Frontend Developer: 80 hours | Frontend Developer: 80 hours
Backend Developer: 80 hours | Backend Developer: 80 hours | Backend Developer: 80 hours
UI/UX Designer: 40 hours | UI/UX Designer: 40 hours | UI/UX Designer: 40 hours
QA Engineer: 40 hours | QA Engineer: 40 hours | QA Engineer: 40 hours
Scrum Master/Product Owner: Part-time | Scrum Master/Product Owner: Part-time | Scrum Master/Product Owner: Part-time
Backlog Items Selected: | Backlog Items Selected: | Backlog Items Selected:
User Authentication and Security | Account Management | Security Enhancements
Task 1: Implement user registration functionality with input validation and encryption for storing passwords securely. | Task 1: Implement UI for linking external accounts securely. | Task 1: Implement additional security checks for user authentication.
Task 2: Integrate multi-factor authentication (MFA) using SMS verification for user logins. | Task 2: Enhance transaction history UI to include filtering and search functionality. | Task 2: Enhance logging and monitoring system for detecting suspicious activities.
Task 3: Set up logging and monitoring to detect and prevent unauthorized access attempts. | Task 3: Develop backend logic for setting up account alerts and notifications. | Task 3: Conduct security audit and implement any necessary fixes.
Account Management | Bill Management | Integration with Third-Party Services
Task 4: Develop UI components to display account balances and transaction history. | Task 4: Design UI for viewing and paying bills online. | Task 4: Integrate with personal finance management APIs for data synchronization.
Task 5: Implement backend logic for transferring funds between accounts. | Task 5: Implement backend logic for scheduling automatic bill payments. | Task 5: Develop API endpoints for linking accounts with payment gateways.
Task 6: Design and implement APIs for linking external accounts securely. | Task 6: Set up notification system for reminding users of upcoming bills.
Additional Functionalities
Payments and Transfers | Customer Support | Task 6: Implement feature to view detailed reports on spending habits.
Task 7: Implement UI for initiating payments to other users or merchants. | Task 7: Implement chat support feature and integrate with existing customer support platform. | Task 7: Develop functionality for analyzing financial data to make informed decisions.
Task 8: Develop backend logic for processing recurring and future-dated payments. | Task 8: Create FAQ section and populate with common questions and answers. | Task 8: Enhance accessibility features based on feedback and audit results.
Task 9: Integrate with payment gateways for wire transfers. | Task 9: Develop UI for submitting and tracking support tickets.
Tasks Breakdown and Assignments:
Tasks Breakdown and Assignments: | Mobile Banking | Frontend Developer: Tasks 1, 6
Frontend Developer: Tasks 1, 4, 7 | Task 10: Develop mobile app UI screens for accessing account functionalities. | Backend Developer: Tasks 2, 4, 5
Backend Developer: Tasks 2, 5, 8 | Task 11: Implement responsive design for various screen sizes and devices. | UI/UX Designer: Tasks related to UI design and wireframes for security enhancements and additional functionalities.
UI/UX Designer: Tasks related to UI design and wireframes. | Task 12: Set up push notification service for sending account activity alerts. | QA Engineer: Testing tasks for each implemented functionality.
QA Engineer: Testing tasks for each implemented functionality.
| Tasks Breakdown and Assignments: | Daily Standup Meetings, Demo and Review, Retrospective, and Additional Notes remain consistent with previous sprints.
Daily Standup Meetings: | Frontend Developer: Tasks 1, 2, 4, 10
Time: 9:00 AM | Backend Developer: Tasks 3, 5, 6
Duration: 15 minutes | UI/UX Designer: Tasks related to UI design and wireframes for customer support and mobile banking.
Purpose: Discuss progress, obstacles, and plans for the day. | QA Engineer: Testing tasks for each implemented functionality.
Demo and Review: | Daily Standup Meetings, Demo and Review, Retrospective, and Additional Notes remain consistent with Sprint 1.
Date: May 13th
Time: 10:00 AM
Duration: 1 hour
Purpose: Review implemented features, gather feedback, and plan adjustments for the remaining sprint duration.
Retrospective:
Date: May 14th
Time: 10:00 AM
Duration: 1 hour
Purpose: Reflect on the sprint, identify what went well and what could be improved, and plan action items for the next sprint.
Additional Notes:
Daily burndown chart will be maintained to track progress.
Continuous communication among team members via Slack or any preferred communication tool.
Any impediments will be raised during daily standups and addressed promptly by the Scrum Master.